## Risk Register
Example : Mobile Banking App | [11 empty] | Status | Categories
Risk ID | Risk Description | Impact | Probability | Category | Risk Raised by | Raised Date | Allocated to | Due Date | Status | Resolution or Action | Response | Open | People
PR-001 | Cannot find developers with required skillset | If we hire resources who don’t have necessary skillset, project quality will suffer | 70% | People | Abdi | 2024-04-17 |  | 2024-05-01 | Open | Consult with the recruitment team or human resource team | Prevent | Assigned | Technology
PR-002 | Team members might have conflicts with each other | Team will not be co-operative and project quality will suffer | 99% | People | Andrea | 2024-04-17 |  | 2024-05-01 | Open | Send team members to conflict management training | Mitigate | In Progress | Cost
PR-003 | Solution that you are planning to implement might not be comptible with client environment | Solution will not work as expected | 50% | Technology | Abdi-Andrea | 2024-04-17 |  | 2024-04-24 | Open | Ensure to find a solution compatible with client environment | Contingency | Closed | Schedule
PR-004 | Stakeholders might change their requirements | Project will not be completed on time and within budget, quality will suffer | 90% | Requirements | Andrea | 2024-04-17 |  | 2024-05-01 | Open | Implement change request management system | Mitigate |  | Scope
PR-005 | loss of customer data due to technical failure | Customer data will be lost | 80% | Data | Sanchita | 2024-04-17 |  | 2024-05-01 | Open | Take regular backups and archive old data | Mitigate |  | Competitors
PR-006 | One of the team members who is leaving the project is quite unhappy and might create conflicts with other team members | Don’t do anyting | 99% | People | Andrea | 2024-04-17 |  | 2024-05-01 | Open | Don’t do anyting | Ignore
PR-007
PR-008 | [11 empty] | Prevent: Eliminates the Risk completely. ‐ Mitigate: Reduces the Impact and/or Probability of the Risk occurring. ‐ Transfer: Transfers the financial impact of the Risk on a third party. ‐ Contingency: Provide for an alternative should the risk materialise. ‐ Accept: No response will be implemented
PR-009
PR-010
PR-011
PR-012
PR-013
PR-014
PR-015
PR-016
Formulas:
Due Date = [Raised Date]+14

## Issue REgister
Example : Mobile Banking App | [11 empty] | Issue Response | Status | Categories
ISsue ID | Issue Description | Impact | Probability | Category | Risk Raised by | Raised Date | Allocated to | Due Date | Status | Resolution or Action | Response | Address | Open | People
PI-001 | Developers donot know Java | project quality will suffer | 100% | People | Abdi | 2024-04-17 | Hussnein | 2024-04-24 | Assigned | Train them | Address | Ignore | Assigned | Technology
PI-002 | [12 empty] | In Progress | Cost
PI-003 | [12 empty] | Closed | Schedule
PI-004 | [13 empty] | Scope
PI-005 | [13 empty] | Competitors
PI-006
PI-007
PI-008
PI-009
PI-010
PI-011
PI-012
PI-013
PI-014
PI-015
PI-016
Formulas:
Due Date = [Raised Date]+7

## Change Request Register
Example : Mobile Banking App w Login Screen, Balance Screen, Statements, Transfer | [12 empty] | Issue Response | Status | Categories
CR ID | Change Request Description | Addl Cost | Addl Time | Impact | Risk Introduced | Category | Raised Date | Raised by | Allocated to | Due Date | Status | Resolution or Action | Address | Open | People
PCR-001 | Increase font size | 500 AUD | 1 day time | Users are struggling to view the app, with increased font size, users will be able to use the app easily | Nothing | Application UI | 2024-04-17 | Andrea | Hussnain | 2024-04-24 | Approved | Increase the font size | Ignore | Approved | Technology
PCR-002 | Change the technology, instead of oracle database we want to use ibm database DB2 | 200,000 AUD | 15 days time | We already have oracle database, but we will have to purchase IBM DB2 | our app might not work with DB2 | Database | 2024-04-17 | Andrea | Hussnain | 2024-04-24 | Rejected | Nothing |  | Rejected | Cost
PCR-003 | [13 empty] | Deferred | Schedule
PCR-004 | [13 empty] | Assigned | Scope
PCR-005 | [13 empty] | In Progress | App UI
PCR-006 | [13 empty] | Closed | Database
Formulas:
Due Date = [Raised Date]+7